## Sheet1
A Web Interface to display Bradford City Council "Assets"
Tasks | Start Date | End Date | Duration | Team Members Assigned
Requirements Document for Client | 2024-02-14 | 2024-02-23 | 7 | All Team Members
Interface Section of Requirments Doc | 2024-03-04 | 2024-03-14 | 8 | Munibah and Subhaan
UML Section of Requirments Doc | 2024-03-04 | 2024-03-13 | 7 | Adiba
LSEPI and Risk Assessment Section | 2024-03-04 | 2024-03-13 | 7 | Ifrah
Data Description Section | 2024-03-03 | 2024-03-13 | 8 | Maariyah and Adaam
Code for Login/Register | 2024-03-01 | 2024-03-15 | 10 | Maariyah and Subhaan
Map Visualisation Code | 2024-02-29 | 2024-03-11 | 7 | Ifrah and Adaam
Database Creation and Bulk Upload | 2024-02-26 | 2024-03-11 | 10 | Adiba, Adaam, Maariyah
HTML for interfaces | 2024-02-29 | 2024-03-08 | 6 | Subhaan
Admin verification | 2024-03-08 | 2024-03-14 | 4 | Bilal
UML Class Diagram | 2024-03-11 | 2024-03-14 | 3 | Adaam
Formulas:
End Date = WORKDAY([Start Date],[Duration])